## Slide 1
CLME+ Sub-Project # 1:
EAF for the Caribbean Spiny Lobster
Ecolobster+
Catalyzing implementation of the Strategic Action Programme for the Caribbean and North Brazil Shelf LME’s (2015-2020)
Second CLME+ Project Steering Committee Meeting
ORGANIZATION OF THE FISHERIES AND AQUACULTURE SECTOR OF THE CENTRAL AMERICAN ISTHMUS
(OSPESCA)

## Slide 2
Introduction
OSPESCA belongs to the Central American Integration System (SICA, for its acronym in Spanish).
Member countries: Belize, Costa Rica, Dominican Republic, El Salvador, Guatemala, Honduras, Nicaragua and Panama.
OSPESCA’s objective is to promote the development of sustainable fisheries and aquaculture, in the framework of the Central American integration process.
OSPESCA implement several projects in the region aimed to promote a better management, governance and sustainable development of fisheries and aquaculture.
Currently, the Ecolobster+ sub-project of the CLME+ is executed by the organization.

## Slide 3
Introduction - Outputs
OUTCOME 1: Expanded and enhanced, interactive and cross-sectorial governance arrangements facilitate full policy cycle implementation, with EAF focus, at (sub)regional and national levels.
Output 1.1. (O1.1.) Expanded and enhanced transboundary governance architecture: OSPESCA, CRFM, WECAFC.
Output 1.2. (O1.2.) Enhanced national-level governance architecture for EAF approach to spiny lobster fisheries management at demo scale (selected CLME+ countries): National fisheries agencies.

## Slide 4
OUTCOME 2: Enhanced capacity for knowledge/data-based management of the Caribbean spiny lobster resource.
Output 2.1. Regional management plan for Caribbean spiny lobster fisheries: WECAFC, OSPESCA, CRFM.
Output 2.2. Enhanced capacity for data collection, stock assessment, management, analysis, reporting & exchange across the regional, sub-regional and national levels: national fisheries authorities, stakeholders.
Output 2.3. Enhanced capacity for Monitoring, Control & Surveillance (MCS): national fisheries authorities, navy and other related authorities.
Output 2.4. Enhanced stock assessment capacity: national fisheries authorities.
Introduction - Outputs

## Slide 5
OUTCOME 3: Socially just management/stress reduction measures implemented and/or in place.
Output 3.1. Regionally coordinated implementation of annual closed season for Caribbean spiny lobster fisheries: WECAFC, CRFM, OSPESCA, national stakeholders.
Output 3.2. Enhanced/coordinated implementation of measures against IUU, tailored to the lobster fishery: WECAFC, CRFM, OSPESCA.
Output 3.3. Implementation & promotion of traceability system for Caribbean spiny lobster fisheries products: OSPESCA, OIRSA.
Output 3.4. Alternative spiny lobster fishing methods tested at the pilot level and potential for replication and up-scaling evaluated: OSPESCA, stakeholders.
Introduction - Outputs

## Slide 6
OUTCOME 4: Mechanism in place to track progress towards EAF and to facilitate adaptive Sub-Project management, replication & up-scaling of activities, and strategy to ensure continuity of efforts beyond the Sub-Project lifespan.
Output 4.1. System to track and evaluate progress towards EAF and to facilitate strategic/adaptive decision-making, adopted and operational: OSPESCA, CERMES.
Output 4.2. Lessons learnt and best practices from the demo activities documented and disseminated among interested CLME+ states and other stakeholders: OSPESCA.
Output 4.3. Additional co-financing leveraged for Sub-Project implementation, and formally adopted Sub-Project after-life plan.
Introduction - Outputs

## Slide 7
Status technical implementation:
Status financial expenditure
On Track | Moderate Delays | Major Delays
 | x | 
On Track | Moderate Delays | Major Delays
 | x | 
If we consider the original time allocation of the Sub-Project was four years.

## Slide 8
Project Implementation Overview
Category | Percentage (Ecolobster+: 40 targets and 13 milestones)
Completed | 7/40 targets (17%)
On track | 16/40 (40%)
Low risk of not completing on time | 3/40 targets (8%)
High risk of not completing on time | 14/40 targets (35%)
High risk of target not being achieved | 

## Slide 9
Achievements to Date
Interim Coordination Mechanism for Sustainable Fisheries (FAO-CRFM-OSPESCA), in place since 2016.
National working groups, focal points in place.
Updated the spiny lobster fishery management plan for the OSPESCA countries, and expanded to the WECAFC region (English and Spanish).
Stock assessment methodology agreed, and designed the data forms for spiny lobster stock assessment.
Support to the execution of the regional closed season for spiny lobster in OSPESCA countries.
Draft paper of a regional traceability standard.
Baseline revision/update of the regional management regulations and legal framework.

## Slide 10
High Risk Targets
Output | High risk of not completing on time | High risk of target not being achieved
Output 1.1. (O1.1) Expanded and enhanced transboundary governance architecture | 100% implementation of the mandates among agencies / institutions (CRFM, WECAFC and OSPESCA) on each of the 7 components of the policy cycle in which they have competence. 100% implementation of current measures that facilitate participation of civil society and private sector actors in the implementation of the lobster policy cycle at the regional level. | 
Output 1.2. (O2.2) Enhanced national-level governance architecture for EAF approach to spiny lobster fisheries management at the demo scale (selected CLME+ countries) | At least 7 CLME+ spiny lobster fishing countries with enhanced national-level architecture that: • Enables full policy cycle implementation • Facilitates cross-sectorial coordination • Facilitates interactive governance; by Sub-Project end. | 

## Slide 11
High Risk Targets
Output | High risk of not completing on time | High risk of target not being achieved
Output 2.1. Regional management plan for Caribbean spiny lobster fisheries | Presentation of the regional management plan to the WECAFC meeting for its consideration. Plan adopted and integrated at national level in at least 7 CLME countries by the end of the project’s third year. | 
Output 2.3. (O2.3.) enhanced capacity for Monitoring, Control and Surveillance (MCS) | Inter-linked regional and national-level vessel register in place and operating in at the least OSPESCA countries plus Colombia, Jamaica and the Bahamas, by the end of the sub-project’s third year. | 

## Slide 12
High Risk Targets
Output | High risk of not completing on time | High risk of target not being achieved
Output 3.1. (O3.1.) regionally coordinated implementation of annual closed season for Caribbean spiny lobster fisheries. | OSPESCA-CRFM agreement, in the context of the Joint Action Plan, on geographic expansion of coordinated closed season implementation. Coordination of closed season implementation with additional relevant lobster stock range countries, as a minimum during the last Sub-Project year. | 
Output 3.3. (O3.3.) implementation & promotion of traceability system for Caribbean spiny lobster fishery products | Regional traceability standard submitted to CLME+ steering committee and WECAFC by year 2. | 

## Slide 13
High Risk Targets
Output | High risk of not completing on time | High risk of target not being achieved
Output 3.4. (O3.4.) alternative spiny lobster fishing methods tested at the pilot level and potential for replication and up-scaling evaluated | Pilot initiative under implementation to test and evaluate sustainable alternative fishing methods by the end of Sub-Project year 1. Technical and economic feasibility evaluated by the end of the Sub-Project´s year 3. Potential for replication and up-scaling analyzed and quantified, linked to socio-economic target indicators, and documented by the end of the Sub-Project’s year 3. | 

## Slide 14
# | Challenge | Mitigative Measure | By When
1 | There is limited progress and participation in Ecolobster+ from extra-regional countries | This issue has been addressed through formal and informal communications from OSPESCA and Ecolobster+ with involved countries. Colombia and Jamaica were visited by Ecolobster+ staff in 2017 to address the issue. The Ecolangosta + coordinator has informed the CLME + PCU of these situations and it has been suggested that the CLME + Director can intercede with GEF focal points in order to solve these longstanding problems. | In progress since 2017
2 | Historical human resources and financial limitations delay work plan implementation. Priorities vary from country to country. | This issue is addressed through communication with national focal points and authorities. Nevertheless, it is an historical structural problem in the fisheries governmental sector. | In progress
Challenges Being Experienced

## Slide 15
Financial Implementation
Agency name | 2018 Budget | Amount spent up to April 2018 | 2019 Budget | Risk of not achieving budget objective | Proposed remedial actions
OSPESCA | US$ 413,162 | US$ 85,766 | US$ 166,241 | Slow implementation of activities in the countries. | Strengthen the monitoring of compliance with the established work plans.
Agency name | Project Budget | Amount spent up to April 2018
OSPESCA | US$ 960,000 | US$ 466,364
Performance | Project | 2018 (April 2018)
 | 48.58 % | 20.76 %

## Slide 16
Crosscutting Recommendations for Successful Project Implementation
Strengthen the participation and work of the national fisheries authorities to achieve the objectives. It is required that the subproject activities are duly incorporated in the national planning process, programs and development plans.
Data collection and analysis systems for decision-making should be strengthened, in particular statistics and databases.

## Slide 17
Crosscutting Recommendations for Successful Project Implementation
Countries need to continue the definition and analysis of indicators, reference points and targets beyond the execution period of the sub-projects.
While cooperation projects, and even government itself, could not solve structural problems in the short term, it is possible to implement actions such as training for officers already working as well as making alliances with other agencies, such as national statistics authorities, universities, research institutes and NGOs, among others.

## Slide 18
Thank You
Catalyzing implementation of the Strategic Action Programme for the Caribbean and North Brazil Shelf LME’s (2015-2020)
Second CLME+ Project Steering Committee Meeting