## Slide 1
Catalyzing implementation of the Strategic Action Programme for the Caribbean and North Brazil Shelf LME’s (2015-2020)
SECOND MEETING OF THE UNDP/GEF CLME+ PROJECT STEERING COMMITTEE, 18-20 JUNE 2018: UWI-CERMES
  SUB-AGENDA ITEM 5.2 – CO-EXECUTING AGREEMENTS IMPLEMENTATION OVERVIEW
Second CLME+ Project Steering Committee Meeting

## Slide 2
Introduction
Promotes and facilitate sustainable development
in the Caribbean and beyond through:
Graduate education
Applied research and innovative projects
Involvement in the national, regional and global initiatives
Professional training

## Slide 3
Introduction
Name of Initiative: KNOWLEDGE MANAGEMENT IN SUPPORT OF THE IMPLEMENTATION OF THE CLME+ STRATEGIC ACTION PROGRAMME
Date CEA entered into force: 01/01/17
Expected date CEA is to be finalized: 31/12/19
List CLME+ Outputs Responsible for:
      1.2 National Inter-sectoral Coordination mechanisms (NICs) in place
      1.3 Regional policies, declarations and/or regulations, and associated national-level legislation and/or plans, are appropriate to enable effective EBM/EAF in the CLME+
      5.1 Cooperation among development partners, programmes, projects, initiatives (PPIs) and countries/territories with a stake in the CLME+ SAP
      5.2 Prototype CLME+ State of the Marine Ecosystems (SOME) and SAP implementation M&E mechanism
      5.3. Communication, twinning and knowledge exchange activities targeting the CLME+ Partnership and global LME Community of Practice

## Slide 4
Status technical implementation:
Status financial expenditure
On Track | Moderate Delays | Major Delays
On Track | Moderate Delays | Major Delays

## Slide 5
Category | Percentage
Completed | ~20%
On track | ~70%
Low risk of not completing on time | ~10%
High risk of not completing on time | ~0%
High risk of target not being achieved | ~0%
Project Implementation Overview

## Slide 6
Achievements to Date
Milestone/Output | Target | Briefly describe (full or partial) achievement
Output 1.2. NICs | T.PI1. Completed baseline analysis. Sustainable NIC mechanisms operating in at least 60% of CLME+ participating countries | Analysis is still in progress. Few functioning NICs in countries, but can relax criteria to near-NICs to reach 60% target. Very low response rate and data difficult to validate.
Output 1.3 EBM-EAF | T.PI1. EBM/EAF concepts and key principles integrated in at least 4 (sub)-regional policies etc. and updated in at least 60% of CLME+ countries. Gender and youth concerns mainstreamed. | First EBM/EAF baseline inventory is done. There is evidence supporting incremental EBM and EAF implementation. Two sub-projects show signs of integration activity. No measurement yet of updating. Gender and youth mainstreaming in early stages.

## Slide 7
Achievements to Date
Milestone/Output | Target | Briefly describe (full or partial) achievement
Output 5.1. PPIs | O5.1. T.PI1. Active involvement of min. 70% of CLME+ countries in Project and SAP implementation up-scaled to 90% by 2019.; T.PI2. Active involvement of min. 33% of CLME+ overseas territories; T.PI3. Active participation of at least 12 organizations with mandates highly relevant to the SAP; T.PI4 At least 30% of PPIs actively engaged in coordinated implementation of the SAP; T.PI5 Total “portfolio”/investment value of USD 350 million | PPI database done. PPIs linked to SAP in the database. PPI database is accessible on the CLME+ website but is not easy to find. No evidence of active, conscious linkages of PPI by design to SAP implementation except in other GEF-funded projects e.g. CC4FISH, REBYC-II LAC, StewardFish, etc. No data yet on investment value of projects that may, by design, contribute to SAP implementation. .

## Slide 8
Achievements to Date
Milestone/Output | Target | Briefly describe (full or partial) achievement
Output 5.2. and Output 5.3 SOMEE and SAP M&E | TO5.2 T.PI1. CLME+ indicator sets, monitoring approaches and/or protocols O5.3.T.PI2. Content developed & online for CLME+ Status and SAP M&E web portal(s) by end of 2017, and first “State of …..” report by at the latest end of 2019 | Indicator sets: fisheries, pollution and habitat degradation at the regional level. Template workbook with test data developed. At the pilot level progress has been slow. SOMEE outline has been developed in collaboration with PCU.
Output 5.3. LEARN | T.PI4 Min. 3 Experience Notes on SAP implementation, and 4 on EBM/EAF in the CLME+ | No experience notes produced. Awaiting sub-project outputs with positive experience

## Slide 9
# | Challenge | Mitigative Measure | By When
1 | Basic information for NIC, PPI and EBM-EAF outputs is not online or available from individuals, partner organisations, national focal points… | Test hiring in-country investigators, aware that such funding is not sustainable beyond the project | After PSC is informed of information constraints, and if it agrees payment for its data is new normal
2 | Low level of awareness or interest in CLME+ SAP constrains extraction of information from respondents | Beyond the scope of CERMES. Needs implementation of active communication campaigns | Soonest if PCU agrees to renewed communication thrust, assisted by PSC
 | Difficult to effectively engage with some sub-projects through their contracted consultants and delays | Partner organisations are being asked to further assist implementation | Soonest organisations are able to facilitate
Challenges Being Experienced

## Slide 10
Agency name | 2018 Budget | Amount spent up to April 2018 | 2019 Budget | Risk of not achieving budget objective | Proposed remedial actions
UWI-CERMES | 55,000 | 17,400 | 55,000 | Moderate | Increased spend (mainly on data)
Financial Implementation

## Slide 11
the end
Catalyzing implementation of the Strategic Action Programme for the Caribbean and North Brazil Shelf LME’s (2015-2020)
Second CLME+ Project Steering Committee Meeting
ditable Text