RECOMMENDATIONS AND DECISIONS OF THE SECOND STEERING COMMITTEE MEETING OF THE CARIBBEAN AND NORTH BRAZIL SHELF LARGE MARINE ECOSYSTEMS PROJECT (UNDP/GEF CLME+ PROJECT)

18 – 20 June, 2018

Panama City, Panama

The CLME+ Project Steering Committee:

Having convened the Second CLME+ Project Steering Committee Meeting in Panama City,  Panama, from 18 -20 June, with a total of 45 participants and Chaired by Panama with the Deputy Chairperson from Trinidad and Tobago and the Rapporteur from Saint Vincent and the Grenadines;

Noting that the Caribbean and North Brazil Shelf Large Marine Ecosystems (hereinafter jointly referred to as “the CLME+ region”) are two of the sixty-six (66) globally defined Large Marine Ecosystems proposed by the National Oceanic and Atmospheric Administration of the United States of America (NOAA) and the Global Environment Facility (GEF) as meaningful geospatial units for the implementation of an Ecosystem-Based Management (EBM) approach and for an Ecosystem Approach to Fisheries (EAF);

Recalling that, with the support from the United Nations Development Programme (UNDP)/GEF Project, “Sustainable Management of the Shared Living Marine Resources of the Caribbean Large Marine Ecosystem and Adjacent Regions” (GEF ID 1032; 2009-2014, hereinafter referred to as “CLME Project”), a 10-year “Strategic Action Programme for the Sustainable Management of the Shared Living Marine Resources of the CLME+ region” (hereinafter referred to as the “CLME+ SAP” or simply as “SAP”) was developed and received high-level political endorsements covering to date a total of 25 countries and 6 overseas territories;

Recalling that the CLME+ SAP provides a comprehensive roadmap towards sustainable living marine resources management through strengthened and consolidated regional cooperation and the adoption of EBM/EAF;

Recognizing that the UNDP/GEF Project, “Catalysing Implementation of the Strategic Action Programme for the Sustainable Management of shared Living Marine Resources in the Caribbean and North Brazil Shelf Large Marine Ecosystems” (GEF ID 5542; 2015-2020; hereinafter referred to as “CLME+ Project”) aims at strengthening and consolidating regional coordination and cooperation through the implementation of the politically endorsed CLME+ SAP;

Acknowledging that the CLME+ Project became operational in May 2015;

Gratefully recognizing the continued commitment of the Global Environment Facility (GEF), the GEF Implementing Agency, UNDP and the Executing Agency, UNOPS, the participating governments, organisations and partners towards the successful implementation of the CLME+ SAP and Project, as well as the Government of Panama for hosting the Meeting;

Commending the CLME+ Project Coordination Unit (CLME+ PCU) in their efforts to successfully organize this Second Project Steering Committee Meeting;

The Meeting:

AGENDA ITEM 5 – OVERALL PROJECT IMPLEMENTATION STATUS

- a. Notes the overview provided by the CLME+ Project Coordination Unit (PCU) and the Co-Executing Agencies (CEA’s) on the status of the CLME+ Project activities, outputs and outcomes.

b. Notes the financial project implementation status presented by the CLME+ PCU and the CEA’s.

c. Notes the challenges and delays in project implementation faced to date, as presented to the meeting by the PCU and the CEAs

AGENDA ITEM 6 – SAP ENDORSEMENTS (New endorsements from Previous SCM)

- Welcomes the new endorsements of the CLME+ Strategic Action Programme from Antigua and Barbuda, Bahamas, France and Montserrat and encourages those countries/overseas territories which have not endorsed the CLME+ SAP to do so.

AGENDA ITEM 7- STATUS OF INTERIM COORDINATION MECHANISMS

- Acknowledges the work of the Sustainable Fisheries and the CLME+ SAP Interim Coordination Mechanisms (ICMs)and expresses continued support for these mechanisms

- a. Notes the current levels of progress with the NIC analysis, including the difficulties in completing the analysis.

b. Agrees that CLME+ Project National Focal Points assist with the collection of information as required to complete the NIC analysis.

Agenda Item 8 – Overview and Status of the Permanent Policy Coordination Mechanism and the Sustainable Financing Plan Consultancy

- a. Notes the progress obtained to date under the Permanent Policy Coordination Mechanism (PPCM) and Sustainable Financing Plan (SFP) Consultancy

b. Acknowledges the critical importance of this consultancy for the enhancement of ocean governance in the CLME+ region.

c. Commit to engage and facilitate consultations at the national level in relation to the proposed Options for the PPCM and SFP in preparation for the regional consultations throughout the consultancy lifespan including the upcoming September 2018 regional consultation.

AGENDA ITEM 9 – CLME+ PARTNERSHIP AND ALLIANCE

- a. Notes the progress obtained to date regarding the creation of a “Global CLME+ Partnership and Alliance for the Sustainable Management, Use and Protection of the CLME+ region” (in short also referred to as respectively the “CLME+ Partnership” and “CLME+ Alliance”)

b. Notes the need to further clarify the role of the countries relative to the Partnership

c. Requests the PCU to liaise with interested Steering Committee members to finalize the Terms of Reference for the CLME+ Partnership

d. Recommends that due consideration is given to the issue of the sustainability of the Partnership

e. Welcomes the efforts of the CLME+ PCU to organize a first CLME+ Partnership Forum in the second semester of 2018

AGENDA ITEM 10 – OVERVIEW OF THE CIVIL SOCIETY ACTION PROGRAMME

- Welcomes the achievement of civil society organisations (CSOs) in developing a draft Civil Society Action Programme which is aligned with and supports CLME+ SAP implementation in achievement of the shared vision.

- Welcomes the ongoing efforts to include other CSOs in the review of the C-SAP and encourages the engagement of key CSOs in the CLME+ region in the C-SAP finalization process

AGENDA ITEM 11 - SAP M&E FRAMEWORK AND SOMEE

- Endorses the conceptual approach for the development and implementation of a SAP Monitoring and Evaluation (M&E) Framework as presented.

- Welcomes the progress to date with the development of an indicator framework for the monitoring of SAP Actions, as well as with the development of the Governance Effectiveness Assessment Framework (GEAF) indicator set, including its anticipated role in the overall evaluation of SAP Implementation

- a. Requests the PCU to continue coordinating fine tuning the M&E Framework, in particular giving due consideration to the need to include both quantitatively and qualitatively, strategically chosen indicators

b. Further requests the PCU to take into account national and regional capacities, and to align M&E indicators with international targets and indicators as appropriate.

- Encourages countries and key IGOs within the CLME+ region to provide feedback on the GEAF indicator set as it is being further developed and integrated as relevant in the SAP M&E framework and the SOMEE reporting process

- a. Acknowledges the SOMEE development approach as presented, as well as its importance for consolidating the CLME+ Regional Framework for Ocean Governance called for under the CLME+ SAP

b. Agrees to support the CLME+ SAP ICM in their efforts to develop and implement the M&E framework and SOMEE reporting process, including providing the best possible available data as appropriate

c. Acknowledges the need to institutionalize the SOMEE mechanism and within this context requests the CLME+ SAP ICM to give further consideration to the issue of core national and regional capacities, including the financial and technical sustainability of the mechanism, as well as the specific roles and expectations of countries.

AGENDA ITEM 12 – MID-TERM EVALUATION CONSULTANCY RESULTS

- a. Acknowledges the preliminary findings of the CLME+ Project Mid-term Evaluation as presented at the Meeting and agrees on the need to accelerate implementation of delayed activities

b. Further acknowledges that notwithstanding the complexity and diversity of the CLME+ project and the region, a multi country cooperation in the application of EBM/EAF is crucial for the continuing health of the transboundary living marine resources of the two LMEs

AGENDA ITEM 13 – CLME+ PROJECT WORKPLAN AND BUDGET

- Approves an initial extension of the project duration till 31 August 2020, to accommodate the delays occurred during the Project Inception Phase

- Approves the amendments to the CLME+ Project Results Framework in alignment with this initial extension, as outlined under CLME+ Project Steering Committee Meeting Document AgendaItem13v180619

- Approves the CLME+ revised budget for the period 1 January 2018 – 31 August 2020 as presented

- Agrees to defer a decision related to a further no-cost extension for the CLME+ Project until the first quarter of 2019, with the understanding that such decision will be based on the review by the Project Steering Committee of the assessment provided by the PCU of implementation progress by 31 December 2018.

- Urges the Co-Executing Partners to submit the information on implementation progress to the PCU by latest 31 December 2018

- a. Requests that the PCU submits a report to the Project Steering Committee during January 2019, detailing, as applicable, (a) the proposed length of the extension, (b) the proposed associated budget revisions, and (c) detailing the anticipated impacts of such revisions on the CLME+ Project Outputs, and requesting their consideration of such proposals

b. Agrees that the Project Steering Committee be given one month to review the proposals and provide their agreement in writing, and acknowledges that any member country that does not respond in writing within the specified timeframe will be understood to be in agreement with the recommendation outlined by the PCU.

- Accept the state of expenditure between 1st and 2nd Project Steering Committee Meeting as presented by PCU and CEAs.

- Acknowledges the implementation of the online project planning and progress dashboards on the CLME+ project website as a tool for the Project Steering Committee to remain informed about project progress and urges the PCU and Co-Executive Agencies to provide three-monthly progress updates through this.

- Acknowledges the usefulness and importance of the periodic reporting model adopted by the co-executing agencies UN Environment and FAO as presented and urges the agencies to continue its systematic use.

- Urges IOC/UNESCO and UNOPS to formalize the UN to UN agreement as soon as possible

AGENDA ITEM 14 – CLME+ COMMUNICATIONS

- a. Approves the 3 focus areas for CLME+ Project communications as presented and requests the CLME+ PCU to further work on the revision of the Project Communication Strategy, in alignment with the identified focus areas and their relative priority

b. Acknowledge the need for enhanced communication flows among the PCU, the Project National Focal Points and Liaison Persons, the Co-Executing Partners, the CLME+ Sub-Project National Focal Points and the IGO National Focal Points with a stake in the CLME+ Project Activities and Outputs, and urges the CLME+ PCU, Co-Executing Partners and Steering Committee Members to engage in establishing such enhanced information flows

AGENDA ITEM 15 – CLME+ HUB

- a. Notes the existence of the CLME+ Project website and the prototype version of the CLME+ Hub, including the associated tools such as the database of projects supporting the implementation of the CLME+ SAP

b. Acknowledges their purpose and usefulness and recommends the PCU and Co-Executing Partners collaborate towards their further development